## give me excel agile doc of this
Planned Sprint | Actual Sprint | US ID | User Story | MOSCOW | Assignee | Dependency | Status
Sprint 1 | Sprint 1 | US-01 | As a developer, I want to set up the project structure so that all modules (chatbot, static analyzer, IP checker, live data) integrate smoothly. | Must Have | Priyanshi , Vishnu | None | Completed
Sprint 1 | Sprint 1 | US-02 | As a user, I want a clean UI home page so that I can navigate all analyzer tools easily. | Should Have | Pratham , Shivam | US-01 | Completed
Sprint 1 | Sprint 1 | US-03 | As a system, I want backend boilerplate setup (API routing, DB config) to support future modules. | Must Have | Shreya , Sanjay | None | Completed
Sprint 2 | Sprint 2 | US-04 | As a user, I want to upload a PDF/Doc/EXE so that the system can statically scan for potential threats. | Must Have | Kanak , Kanupriya | US-03 | Completed
Sprint 2 | Sprint 2 | US-05 | As a system, I want to extract metadata & readable text from uploaded files so I can perform static ML analysis. | Must Have | Kanak , Kanupriya | US-04 | Completed
Sprint 2 | Sprint 3 | US-06 | As a user, I want a chatbot that answers my cybersecurity questions using the trained ML model. | Could Have | Priyanshi , shreya | US-03 | Completed
Sprint 2 | Sprint 3 | US-07 | As a user, I want the chatbot UI integrated into the dashboard for fast access. | Could Have | K S Vamsi , Manoj Kumar | US-06 | Completed
Sprint 3 | Sprint 4 | US-08 | As a user, I want to input an IP to get threat intelligence (e.g., blacklist status). | Must Have | Sanjay , Kanak , Priyanshi | US-03 | Completed
Sprint 3 | Sprint 4 | US-09 | As a user, I want live file monitoring so suspicious behavior can be tracked in real time. | Should Have | Praham , Shivam | US-05 | Completed
Sprint 3 | Sprint 4 | US-10 | As a system, I want to fetch external threat intelligence APIs for enhanced IP scoring. | Could Have | Shreya , Vishnu | US-08 | Completed
Sprint 4 | Sprint 5 | US-11 | As a system, I want to generate a threat score (Low/Medium/High) for uploaded files. | Must Have | Priyanshi , Kanupriya | US-05 | Completed
Sprint 4 | Sprint 5 | US-12 | As a user, I want a detailed threat analysis report to understand risks. | Must Have | Pratham , Shivam | US-11 | Completed
Sprint 4 | Sprint 5 | US-13 | As a user, I want the dashboard to display all results in unified format. | Should Have | kanak , shivam | US-12 | Completed
Sprint 4 | Sprint 5 | US-14 | As a system, I want to store analysis history in database. | Could Have | vishnu , sanjay , shreya | US-11 | Completed
Sprint 5 | Sprint 6 | US-15 | As a user, I want all modules (chatbot, static scan, live scan, IP checker) integrated into a single platform. | Must Have | Priyanshi , Shreya , kanak | All previous | Completed
Sprint 5 | Sprint 6 | US-16 | As a tester, I want system-wide testing so that bugs are minimized. | Must Have | vishnu , sanjay , kanupriya | US-15 | Completed
Sprint 5 | Sprint 6 | US-17 | As a user, I want final UI/UX polishing. | Could Have | Pratham , Shivam , Manoj , Ks Vamsi | US-15 | Completed
Sprint 5 | Sprint 6 | US-18 | As a student team, we want deployment documentation prepared. | Should Have | All Members | US-16 | Completed